## RLS
|  | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
|  | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23
Offshore | # Resource | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 180 | Total Man days
| Hours | 87.5 | 175 | 175 | 175 | 175 | 131.25 | 131.25 | 131.25 | 131.25 | 131.25 | 131.25 | 1575 | Total hrs
Onshore | # Resource | 0.2 | 0.25 | 0.15 | 0.25 | 0.15 | 0.15 | 0.15 | 0.15 | 0.25 | 0.15 | 0.15 | 10
| Hours | 8 | 10 | 6 | 10 | 6 | 6 | 6 | 6 | 10 | 6 | 6 | 80 | Total hrs
TCoE Governance | # Resource | 0.25 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.15 | 0.1 | 0.1 | 11.5
| Hours | 10 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 6 | 4 | 4 | 92 | Total hrs
Wkly Target | #script Count | 0 | 15 | 22 | 23 | 24 | 23 | 24 | 23 | 24 | 23 | 0 | 201 | Total Scripts
Script Development Milestones | Script Delivery Week | 2016-03-14: Script Delivery Date; 2016-03-21: Total Script To be Delivered; 2016-03-28: Man Days Planned; 2016-04-11: > Week 0 is for resource onboarding, app learning and planning. > Last week (Week 10) is kept as buffer for pending tasks and dry run. > All development should be completed by June when E2E 2nd cycle will begin.
Milestone 1 | 2016-04-04 | 2016-03-14: 2016-04-08; 2016-03-21: 60; 2016-03-28: 60
Milestone 2 | 2016-04-18 | 2016-03-14: 2016-04-22; 2016-03-21: 47; 2016-03-28: 35
Milestone 3 | 2016-05-02 | 2016-03-14: 2016-05-06; 2016-03-21: 47; 2016-03-28: 30
Milestone 4 | 2016-05-16 | 2016-03-14: 2016-05-20; 2016-03-21: 47; 2016-03-28: 30
TOTAL |  | 2016-03-21: 201; 2016-03-28: 155

## Script Development
ParMed Web Automation
Total # of TCs | 201 |  | % Automatable | 100%
# of TCs to be Automated | 201
Complexity |  |  |  |  | Assumption
Definitions | Medium | Low |  |  | Scope for testing and given script count is for Parmed Web only. However, when Automation is taken up, the script count might change based on new changes and code changes in PMOD environment due to other parmed projects.
Number of GUI Controls | 16 to 30 | <=15
Number of Test Steps in TCs | 17 to 29 | <= 16
Number of Screens | 05 to 08 | <=04
Effort | Medium | Low | Total |  | Other Efforts | %
% of TCs in Each Category | 68.66% | 31.34% | 100% |  | Test Data Effort | 2%
# TCs in Each Category | 138 | 63 | 201 |  | Automation Suite execution | 8%
Development Effort (hrs/script) | 7.5 | 4 |  |  | Review Effort | 8%
Total Effort (Hours) | 1035 | 252 | 1287 |  | Integration Effort | 5%
[5 empty] | Test Management Effort | 5%
Automation Development
Activities |  | Effort (Hours) |  | Comments
Application Study |  | 35 |  | Effort for understanding the application and manual test scripts
Test Planning and Strategy |  | 35 |  | Added as per discussion with Deepak.
Script Development |  | 1287 |  | From the table above.
Review Effort |  | 102.96 |  | 8% of Script Dev
Integration Effort |  | 64.35 |  | UFT, ALM integration , test case setup, mapping etc.
Test Data Effort |  | 25.74 |  | 2% of Script Dev
Automation Test suite execution |  | 102.96 |  | 8% of Script Dev
Test Management Effort |  | 80 |  | Onshore Effort for Test Management and Tracking
Test Governance |  | 92 |  | Automation CoE effort. Added as per discussion with Deepak.
Total Effort (Hours) |  | 1825.01
Total $ |  | 46970.22
UFT Effort estimated before (hrs) |  | 2245
Cost using UFT ($) |  | 49390
Percentage Saving on UFT |  | 4.899%

## Script Maintenance
Requirement & Impact Analysis
No. Of Requirement/ Changes | Impact Analysis Effort (Hrs)
- | 8.75
Estimate For Maintenance
Total Number of Scripts | Impacted Scripts (Assuming 30%) | Script Maintenance Efforts (Hrs) | Dry Run Effort (Hrs) | Review Effort (Hrs) | Total Maintenance Efforts (Hrs) | Should we add COE hours here?
201 | 60.3 | 72.36 | 3.618 | 3.618 | 79.596
Total Maintenance Effort considering 1 Maintenance cycle (hrs) | 88.346
Cost ($) for 1 cycle | 1943.612
Total Maintenance Effort considering 3 Maintenance cycles (hrs) | 265.038
Cost ($) for 3 cycles | 5830.836
Estimate For Manual Maintenance
Total Number of Scripts | Impacted Scripts (Assuming 30%) | Script Maintenance Efforts (Hrs) | Dry Run Effort (Hrs) | Review Effort (Hrs) | Total Maintenance Efforts (Hrs)
230 | 69 | 28.75 | 0 | 1.4375 | 30.1875
Note on C3: Considering 10 Mins Per requirement
Note on C4: Dattagupta, Aritra: Since changesin E2E will be defect fixes, a ballpark value of 2PD is considered for impact analysis. This is aligned with 30% impact considered on impacted scripts.
Note on D7: Considering 2 Hrs Per Scripts
Note on E7: 10% of Maintenance Effort
Note on F7: 10% of Maintenance Effort
Note on D21: Considering 2 Hrs Per Scripts
Note on E21: 10% of Maintenance Effort
Note on F21: 10% of Maintenance Effort

## Script Execution
AUTOMATION TEST EXECUTION
Estimate For Data Setup |  | Estimation For Execution
Total Number of Scripts | Total efforts(Hrs) | Total Number of Scripts | Total Efforts (Hrs)
201 | 8.75 | 201 | 35
Total Execution Effort (Hrs) for 1 Cycle | 43.75
Total Execution Effort (Hrs) for 5 Cycles | 218.75
Cost ($) for 5 cycles | 4812.5
Cost (for 1 cycle | 962.5
MANUAL TEST EXECUTION
Estimate For Data Setup |  | Estimate For Execution
Total Number of Scripts | Total efforts(Hrs) | Total Number of Scripts | Total efforts(Hrs)
230 | 8.75 | 230 | 147.5833
Total Execution Effort (Hrs) for 1 Cycle | 156.3333
Total Execution Effort (Hrs) for 5 Cycles | 781.6667
Cost ($) | 17196.6667
Cycle Time Reduction | 72.01%
Note on C4: Considering 3 Min/Scripts
Note on E4: Considering 30 Scripts/Day
Note on C18: Considering 5 Min/Scripts
Note on E18: Considering 5 Min/Scripts