## ITG_ParMed
| Rate | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Total
Resources |  | 03/14 - 03/18 | 03/21 - 03/25 | 03/28 - 04/01 | 04/04 - 04/08 | 04/11-04/15 | 04/18-04/22 | 04/25-04/29 | 05/02-05/06 | 05/09-05/13 | 05/16-05/20 | 05/23-05/27 | 05/30-06/03 | 06/06-06/10 | Resource Wise Hours
Aritra(Onsite) | 66.3 | 8 | 10 | 6 | 10 | 6 | 6 | 6 | 6 | 10 | 6 | 6 | 0 | 0 | 80
TBD (Onsite) | 0 | [13 empty] | 0
Rahul Shaw(Offshore) | 21 | 43.75 | 26.25 | 43.75 | 43.75 | 35 | 8.75 | 35 | 43.75 | 43.75 | 43.75 | 43.75 | 43.75 | 43.75 | 498.75
Ashish Kumar Sahoo(Offshore) | 21 | 43.75 | 26.25 | 26.25 | 43.75 | 26.25 | 43.75 | 35 | 43.75 | 43.75 | 43.75 | 0 | 43.75 | 43.75 | 463.75
Sarita Yadav(Offshore) | 21 | 0 | 0 | 43.75 | 43.75 | 35 | 43.75 | 35 | 43.75 | 43.75 | 0 | 0 | 35 | 0 | 323.75
Astika Mohinta(Offshore) | 21 | 0 | 0 | 43.75 | 43.75 | 35 | 43.75 | 35 | 43.75 | 43.75 | 0 | 0 | 0 | 0 | 288.75
| 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 resource 3 wk
0
0
0
0
0
0
0
0
0
0
0
Expected Week Wise Total Hours |  | 95.5 | 62.5 | 163.5 | 185 | 137.25 | 146 | 146 | 181 | 185 | 93.5 | 49.75 | 122.5 | 87.5 | 1655
Expected Cumulative Hours |  | 95.5 | 158 | 321.5 | 506.5 | 643.75 | 789.75 | 935.75 | 1116.75 | 1301.75 | 1395.25 | 1445 | 1567.5 | 1655
Actual Week Wise Total Offshore Hours |  | 0 | 0 | 0 | 0 | 385 | 218.75 | 236.25 | 131.25 | 113.75 | 85 | 43.75 | 87.5 | 131.25 | 1432.5
Actual Cumulative Hours |  | 0 | 0 | 0 | 0 | 385 | 603.75 | 840 | 975.25 | 1094 | 1179 | 1226.75 | 1319.25 | 1458.5
Expected Week Wise Cost |  | 2367.9 | 1765.5 | 3705.3 | 4338 | 3154.05 | 3337.8 | 3337.8 | 4072.8 | 4338 | 2235.3 | 1316.55 | 2572.5 | 1837.5 | 38379
Expected Cumulative Cost |  | 2367.9 | 4133.4 | 7838.7 | 12176.7 | 15330.75 | 18668.55 | 22006.35 | 26079.15 | 30417.15 | 32652.45 | 33969 | 36541.5 | 38379
Actual Week Wise Cost |  | 0 | 0 | 0 | 0 | 8085 | 4593.75 | 4961.25 | 3021.45 | 2720.25 | 1785 | 1183.95 | 2169 | 3286.65 | 26350.65
Leave/Holiday Adjustment Hours |  | 0 | 35 | 17.5 | 0 | 43.75 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 131.25
Need to Adjust Hours |  | 95.5 | 158 | 321.5 | 506.5 | 258.75 | 186 | 95.75 | 141.5 | 207.75 | 216.25 | 218.25 | 248.25 | 196.5 | 2405.75
Actual Week Wise Total Onsite Hours |  | Week 7: 4; Week 8: 5; Week 9: 0; Week 10: 4; Week 11: 5; Week 12: 8 | 26
Week Wise Test Case Deliverables - Automation |  | 0 | 12 | 35 | 60 | 85 | 110 | 135 | 160 | 185 | 201 | Review Complete |  |  | 201
Actual |  | Week 0: 0; Week 1: 12; Week 2: 35; Week 3: 60
Week Wise Test Case Deliverables - Manual (New Dev + Optimization)
87.5
Highlights
1. Total Onsite Hours : 320
2. Total Offshore Hours : 1662.5
3. Total Planned Manual Test Case count is 190
4. Total Planned automation test case count is 114
5. All the 190 manual test cases are planned to be finished by 20th of Nov.
6. All the automation test cases are planned to be finished by 18th Dec.
7. Review+Sign-Off hours mentioned in above two points are included in Test Development hours
8. An additional 48 hours are allocated for incorporation of review comments.
9. An additional 50 onsite hours are dedicated for KA over and above the testing estimates
Note on H6: Rahul Shaw would be working for SPS Lite for 4 working days
Note on G7: Ashish is on leave on 15th Apr
Note on G28: Aritra:-Estimated:- Actual:- Rahul:-Estimated:-192.5 Actual:-87.5 Ashish:- Estimated:-166.25 Actual:-87.5 Sarita:-Estimated:-122.50 Actual:-122.50 Astika:-Estimated:-122.50 Actual:-87.5
Note on H28: Aritra:-Estimated:- Actual:- Rahul:-Estimated:-201.5 Actual:-175 Ashish:- Estimated:-210 Actual:-175 Sarita:-Estimated:-166.25 Actual:-166.25 Astika:-Estimated:-166.25 Actual:-87.5
Note on I28: Aritra:-Estimated:- Actual:- Rahul:-Estimated:-236.25 Actual:-236.25 Ashish:- Estimated:-245 Actual:-245 Sarita:-Estimated:-35 Actual:-35 Astika:-Estimated:-201.25 Actual:-157.5
Note on J28: Aritra:-Estimated:- Actual:-4 hrs Rahul:-Estimated:-52.5 Actual:-0 Ashish:- Estimated:-43.75 Actual:-43.75 Sarita:-Estimated:-43.75 Actual:-43.75 Astika:-Estimated:-245 Actual:-201.25
Note on K28: Aritra:-Estimated:- Actual:- Rahul:-Estimated:- Actual:-35 Ashish:- Estimated:- Actual:-8.75 Sarita:-Estimated:-43.75 Actual:-43.75 Astika:-Estimated:- Actual:-26.25
Note on L28: sarita:-43.75 Ashsih:-23.75 Rahul:-17.5
Note on M28: sarita:-43.75
Note on N28: Ashsih:-43.75 Sarita:-43.75
Note on O28: sarita:-43.75 Abhishek:-87.5
Note on D33: 24th and 25th wipro Offshore Holiday
Note on E33: 28th and 29th March Ashish Sahoo's Leave
Note on G33: 14th April wipro holiday
Note on I33: Monday(25th april) holiday in KDC
Note on I34: Offshore lack hrs 43.75 till this wk
Note on J35: Aritra 4 hrs