## Sheet1
Activities | Effort (Hours) | Activities | Effort (Hours) |  | Activities | Count | Effort(hrs) | Projected Cost($)
Application Study | 35 | Total Estimated Offshore Hours | 1653.01 |  | Estimated Test scripts | 201 | 1655 | 38379
Test Planning and Strategy | 35 | Total Estimated Onsite Hours | 80 |  | Tentative Test scripts delivery excluding Out of scope | 138 | 1138 | 26602.8
Script Development | 1287 | Total Offshore Hours Charged till last week(10th June) | 1432.5 |  | Additional of Maintenance of 84 Scripts | 84 | 157 | 3297
Review Effort | 102.96 | Total Onsite Hours Charged till last week(10th June) | 26 |  | Total hrs should be charged including Maintenance |  | 1295 | 29899.8
Integration Effort | 64.35 | Hrs left to be adjusted(for Abhishek Gupta) | 131.25
Test Data Effort | 25.74 | Offshore Efforts Remaining | 89.26
Automation Test suite execution | 102.96 | Onsite Efforts Remaining | 54
Test Management Effort | 80 | Total ($) Consumed | 34562.55
Test Governance | 92 | Remaining $ | 5454.66 |  | New Scripts |  | 21
Total Effort (Hours) | 1825.01
Total $ | 46970.22 | Activities | Effort (Hours) |  | Activities | Effort (Hours)
|  | Application Study | 35 |  | Application Study | 12
|  | Test Planning and Strategy | 35 |  | Test Planning and Strategy | 12
|  | Script Development | 1287 |  | Component Development | 110
|  | Review Effort | 102.96 |  | Review & Implementation Effort | 30
|  | Integration Effort | 64.35 |  | Integration Effort | 30
|  | Test Data Effort | 25.74 |  | Test Data Effort | 30
|  | Automation Test suite execution | 102.96 |  | Automation Test suite execution | 32
|  | Test Management Effort | 80 |  | Test Management Effort | 0
|  | Test Governance | 92 |  | Test Governance | 0
|  | Total Effort (Hours) | 1825.01 |  | Total Effort (Hours) | 256
|  | Total $ | 46970.22 |  | Total $ | 5376
[5 empty] | Efforts(PD) | 29.2571
|  | ParMed |  | Complexity
|  | Total Scripts | Scripts Impacted | High | Medium | Low
|  | 139 | 55 | 0 | 55 | 0
|  | Average Maintenance Productivity (PD) |  | 2 | 4 | 6
|  | Activities |  | Effort (Hrs.)
|  | Maintenance Effort Required |  | 0 | 120.3125 | 0
|  | Total (Hrs.) |  | 120.3125
|  | Test Data Setup |  | 5.5
|  | Dry Run From ALM |  | 9.1667
|  | Total Efforts Required(hrs) |  | 134.9792
|  | Total Efforts Required(PD) |  | 15.4262